# DETAILED TASKS, ACTIVITIES, AND OUTPUTS

Based on the specific scope of work provided in the TOR, the TACT intends to assist DBP attain its objectives by undertaking the following project tasks and activities.

While the TOR has provided two major phases of project implementation, it is expected that some of the tasks and specific activities are interrelated and will depend on the completion or outputs of the other tasks and activities.  At the same time, some tasks and activities can be simultaneously implemented thereby creating more impact in the implementation of the project, and at the same time maximizing the project resources.  Figure 5-1 shows the project road map, where the linkages and parallel tasks and activities are shown during specific periods of the project.  This is followed by a discussion of the details of approach and methodology for each of these tasks and activities.

Figure  5-1.  Project Implementation Flowchart

Task 9-b. Sub-Project Monitoring

Project Preparation

Project Implementation and Monitoring

Task 3. Project Promotions and Roadshows

Task 4. Conduct of Policy Dialogues

Task 5. Inter-agency Linkages and Coordination

Task 9-a. Project Monitoring and Reporting

Task 7. Technical Support on Sub-Project Evaluation and Processing

Task 6. Technical Support on Sub-project Marketing

Task 8. Technical Assistance to End-users and/or Potential End-users

Task 10. Capacity Building

OUTPUTS:

Rapid Assessment Report

Strategic Marketing Plan

Project Implementation Plan

M&E System, MIS

Promotion Plan

Sub-sector Guidelines, Evaluation Manual, Evaluation Criteria, other evaluation tools

Task 2.  Design of the Implementation Plan

Task 1.  Strategy Formulation

As shown above, the tasks and activities are grouped into the two major stages, the project preparation and project implementation and monitoring, as stated in the TOR. There is also an expected overlap of some activities in both stages.  In particular, considering that there are already about 18 approved sub-projects, sub-project performance monitoring will need to be conducted while several phase 1 tasks are being done. Detailed schedules of these tasks and the expected outputs are presented in Section 6, Work Plan and Deliverables.

## Project Preparation

Activities in this phase are grouped into two major tasks, the strategy formulation and the design of the project implementation plan.  The TACT intends to come up with sub-teams to handle these two tasks simultaneously.  The DPM will have overall responsibility in ensuring that these two tasks and the various activities are conducted as planned; and that the expected deliverables are produced.

### Task 1.  Strategy Formulation

The strategy formulation will have two major activities: 1) conduct of rapid assessment of the five sub-sectors; and 2) preparation of strategic marketing plan.

Activity 1.1	Conduct of Rapid Assessment

The assessment will cover investment opportunities, key players, market, institution and policy status and needs, economy, technologies, and other important areas aspects of the transport and logistics sector.  Emerging technologies will also be looked at, as well as, the experiences and trends in other countries, particularly the ASEAN member countries.  Models of public-private partnerships will also be reviewed and possible PPP structures will be recommended. An assessment report will be produced by the TACT that will provide DBP LPT a report on the current status of the five sub-sectors in terms of the areas specified above.

The assessment will be able to identify extent of development and need in each subsector of the logistics and transport infrastructure by region. The report will include the participation of the private sector key players and the government agencies in the development of the logistics and transport infrastructure in the country and each region.

Activity 1.2	Preparation of Strategic Marketing Plan

Based on the results of assessment, the TACT will draft a strategic marketing plan as to how LIDP can be promoted in the target areas.  The marketing strategy will not only provide detailed marketing approach, but will also include recommendations on specific policy reforms that may be needed in order to promote the Project. Aside from the five sub-sectors already identified, the Consultant Team may look at other sub-sectors with the intention that these sub-sectors will also be in support of the government’s development objectives and strategies. While an initial promotions plan will be prepared simultaneously with the rapid assessment, the strategic marketing plan will contain an updated and improved promotions plan.

The marketing plan will not just identify the key play or target client in each subsector but also competitors (commercial banks) that are also lending to the target subsector. The Plan will be able prescribe strategies on how to position LIDP of DBP in addressing the financing need/requirements of each subsector.

The TACT Sub-Team will be composed of a Marketing Specialist, a Transport Planner/Specialist, a Logistics Planner/Specialist, and an Institutional Specialist.  The Transport Planner/Specialist will take the lead in rapid assessment, while the Marketing Specialist will prepare the Strategic Marketing Plan. The international Project Manager will provide persepective from other countries particularly on emerging technologies and practices. Key informant interviews, focus group discussions, and other forms of data gathering will be done by the Team.  To get a “buy-in” of the strategy, the Team will work with the Bank’s marketing group aside from the LPT.  All activities will be done through the LPT.

The Team will prepare the draft strategy, which will be subjected to a one-day workshop with DBP and other concerned groups, before it is finalized.  The marketing strategy will then be adopted for use by the Project Team (LPT and TACT).  The strategy will be reviewed annually to determine if it has indeed provided the right directions, and if needed, certain adjustments will be made.

| OUTPUTS: | - Rapid Assessment Report - Strategic Marketing Plan |
| --- | --- |
| TIMELINE: | End August – end October 2011 |

### Task 2.   Design of the Implementation Plan

It is important to note that the outputs of the strategic marketing plan will be important inputs to the design of the implementation plan.  However, considering that the Bank has been continuously marketing the Project for the past years, the TACT will need to start preparing some basic documents and guidelines that will be used for the project. This task will be divided into 2 activities, preparation of sub-project management and monitoring tools, and preparation of project implementation plan.

Activity 2.1:  Preparation of sub-project management and monitoring tools

Sub-activities will include:

- Review of the Project’s Operating Policy Guidelines (OPG) to recommend improvements, as necessary

- Review of current sets of documents used by DBP for project evaluation and monitoring.  This will include the Project Evaluation and Endorsement Report (PEER) and the Performance Monitoring and Evaluation Report (PMER) for on-going projects.

- Review of other project OPGs and relevant policies, guidelines, guidebooks, and technical manuals developed through other projects, such as those from EISCP, SLDP, etc.

- Determine gaps on the management and monitoring tools

Based on these reviews, prioritization of which tools are immediately needed will be done by LPT and the TACT. The TACT will recommend which forms and guidelines may be initially adoption in order to facilitate processing of sub-projects that are already available for evaluation or monitoring.  Initially, the TACT intends to prepare technical evaluation guides and performance monitoring guides for the two target sectors, transport and logistics so that the LIDP project team will immediately have the guide and forms to use.  These forms and documents will be improved and revised as necessary as the sub-Project Evaluation and Monitoring activities (Task 7 and Activity 9.2) progresses.  Specific sub-sector evaluation and monitoring guides will be prepared by 2012.

All of the draft outputs of the Sub-sector Specialists will be submitted to LPT and discussed in workshops (half-day or longer) to get inputs and comments from the LPT and other concerned sectors within the Bank.  The Bank may decide, upon recommendation of the TACT if other government agencies and stakeholders will be invited to these meetings and workshops.

| OUTPUTS: | - Revised/Improved Project OPG - Technical Evaluation Guides for the Transport Sector and Logistics Sector, and for the five sub-sectors - Performance Monitoring Guide for the Transport Sector and Logistics Sector, and for the five sub-sectors - New policies, guidelines, guidebooks, and manuals, including evaluation criteria, documentation of best practices and developmental impact, and templates on financial, economic, environmental, and social analyses applicable to LIDP sub-projects (as may be identified) |
| --- | --- |
| TIMELINE: | End of August to end of September for 2011 for the Revised OPG and to October 2011 for the first set of guides By mid 2012 for the specific sub-sector guides and others that maybe identified later |

Activity 2.2:  Preparation of Project Implementation Plan

The Project Implementation Plan will be prepared by the team using the results of rapid analyses and simultaneously with the strategic marketing plan.  The implementation plan will contain detailed tasks and activities, deliverables, and schedule of such tasks and activities. Roles and responsibilities of the key players (TACT, LPT, other DBP offices, PFIs, DBP clients, and other stakeholders and project partners) will also be included.  Resources needed such as estimated budget, supplies and equipment, and other tools will be specified.

The DPM will take the lead in doing this Activity and will work together with the LPT in finalizing the implementation plan.

The project implementation plan will be reviewed after a year for improvement and updating based on the actual activities already undertaken.

| OUTPUTS: | Project Implementation Plan |
| --- | --- |
| TIMELINE: | End of August to end of September 2011 |

## Project Implementation and Monitoring

The Project Implementation and Monitoring phase will have the following tasks:

- Project Promotions and Roadshows

- Inter-agency Linkages and Coordination

- Conduct of Policy Dialogues

- Technical Support on Sub-project Marketing

- Technical Support  on Sub-project Evaluation and Processing

- Technical Assistance to End-users and/or Potential End-users

- Project Monitoring and Reporting

- Capacity Building

These tasks are focused on assisting DBP in promoting the loan facility to finance investments in infrastructure and logistics facility in the country, through project promotion, inter-agency coordination, sub-project management and monitoring, and training of both DBP and PFI staff and end-users and target clients.

As shown in the implementation flowchart, some of the tasks and activities under this phase will be undertaken simultaneously with Phase 1 tasks and activities.

### Task 3.  Project Promotions and Roadshows

This task will have the following activities:

- Preparation of a Promotions Plan and Preparation of Marketing Materials

- Conduct of Regional Industry Conferences

- Participation in Industry Associations’ Conferences

- Conduct meetings and presentations with concerned Government Agencies

Activity 3.1	Preparation of a Promotions Plan

The TACT will prepare a provisional Project Promotions Plan that will provide details on the type of promotional activities to be undertaken, the schedules, and target audience/clients.

The promotion plan will contain information on the type of promotions that will be conducted (conferences, meetings, presentations) and schedules of these activities.  Also to be prepared will be the promotional materials such as brochures and leaflets about the projects.

The promotions plan will be reviewed and revised as needed after the Strategic Marketing Plan (produced under Task 1) is accepted by the LPT.  As discussed during the July 20 meeting, priority will be on getting 2 clients for the packaging, transport and distribution facilities, and 1 client for cold chain.

The Marketing Specialist and the DPM with inputs from the sub-sector specialist will work out the initial plan, including the project brochures and other materials.

| OUTPUTS: | - Project Promotions Plan - Marketing Brochures |
| --- | --- |
| TIMELINE: | End of August – End of September 2011 for the initial promotions plan End of October 2011 for the complete promotions plan (included in the Strategic Marketing Plan |

Activity 3.2.   Conduct of Regional Industry Conferences

Considering the various types of clients and types of investments that are the focus of the Project, the TACT intends to develop promotional activities that are investment-focused on a regional scale.  This means that activities will be prepared per target sub-sector and will be conducted on a regional scale.  If possible, simultaneous or parallel promotion activities will be done at specific regional hubs.

Depending on the results of the rapid assessment, the TACT will determine which regional hub will be the first venue of the conference.

| OUTPUTS: | - Regional Industry Connferences (4 regional hubs – Metro Manila, Luzon, Visayas, Mindanao) - Activity Reports |
| --- | --- |
| TIMELINE | 1 regional conference by November 2011 Other conferences by the first semester 2012 |

Activity 3.3	Participation in Industry Associations’ Conferences

The TACT has an initial list of industry associations whose memberships and concerns are on RRTS vessels and facilities, toll roads, LGU roads, and maintenance equipment, packaging, transport and distribution facilities, cold chain, and bulk chain.

Through the rapid assessment (Task 1, Activity 1.1), the TACT will gather relevant information about these industry associations, including their membership, how active is the association, and what are their activities where LIDP can come in and coordinate with them.  As may be needed and depending on their activities, these industry associations will be visited by the TACT and LPT. The TACT will check on possible participation of the project in industry annual conferences, which may include paper presentations, focus group discussions, or exhibits.

| OUTPUTS: | - Presentation in Industry Association Conferences - Activity Reports |
| --- | --- |

Activity 3.4	Conduct meetings and presentations with concerned Government Agencies

The TACT will coordinate with concerned government agencies, industry and business organizations, and various other concerned groups on infrastructure and logistics sector, particularly the five sub-sectors covered by the project to gather initial information.  The visit will be three-pronged – to gather relevant data and information, to determine areas of possible collaboration and to discuss how DBP can actively participate in policy discussions and development. (Note: this is part of the data gathering for the rapid assessment to be done under Task 1, Activity 1.1).

| OUTPUTS: | - Meetings with Concerned Government Agencies - Activity Reports |
| --- | --- |
| TIMELINE: | Continuing activity but will be initiated by September 2011 |

### Task 4. Inter-agency Linkages and Coordination

It is important that at the onset, the LIDP Team (LPT and TACT) will have established a good relationship with the various agencies involved in infrastructure development.  The TACT will organize meetings and focus group discussions with concerned agencies to develop the relationship insofar as LIDP is concerned. (Part of Task 1. Strategic Planning)

This will be sustained through regular coordination meetings and invites of the concerned agencies including their regional offices, in Project activities.  Whenever possible, the TACT and LPT will conduct courtesy calls to regional offices that has jurisdictions over the LIDP sub-projects, whether on-going or pipeline.

| OUTPUTS: | - Inter-agency coordination meetings - Activity Reports |
| --- | --- |
| TIMELINE: | Continuing activity but will be initiated by September 2011 |

### Task 5. Conduct of Policy Dialogues

This task will have two major activities: the development of policy papers and conduct of policy dialogues.  The main purpose of this task is to contribute to the attainment of the government’s objectives for the sector, which can eventually ease the promotion of LIDP loan facility.

Activity 5.1	Development of Policy Paper

Based on the results of the rapid assessment and development of the strategic marketing plan (Task 1), the TACT will develop Policy Papers that will help DBP push investments in the sectors covered by LIDP.  Selection of focus areas/topics of the Policy Paper/s will be discussed and agreed upon with LPT.

Some initial policy areas that may be pursued by DBP may include the development of the National Logistics Master Plan or the review and redesign of RRTS scheme that was recently suspended/cancelled by the government.  TACT will also provide assistance to DBP in their participation in the development of the National Transport Plan.

Within DBP, the TACT also recommends the review of DBP policies and guidelines that are relevant to LIDP. Coordination and discussions with relevant offices and sectors within the Bank will be done. Results of the policy study/ies will be presented to management after dialogues are conducted within DBP. Appropriate recommendations will be prepared and as maybe needed, new policy directions will be prepared by the TACT and LPT for consideration of the Bank.

| OUTPUTS: | Policy Papers |
| --- | --- |
| TIMELINE: | Month of November 2011 for the first Policy Paper Other Policy Papers to be determined later based on results of rapid assessment and strategic marketing plan |

Activity 5.2	Conduct of Policy Dialogues

The Policy Papers will be subjected to dialogues with the concerned NGAs, industry groups, investors, and other key players of the sector.  Results of the dialogue will be used by DBP to pursue policy changes and improvements.

| OUTPUTS: | - Policy Dialogues - Activity Reports |
| --- | --- |
| TIMELINE: | Month of November 2011 for the first Policy Paper dialogues Other dialogues to be scheduled depending on the Policy Papers identified |

### Task 6.  Technical Support on Sub-project Marketing

The TACT, with the LPT, will conduct meetings with the concerned groups within the Bank to discuss the Promotions Plan and the Strategic Marketing Plan, and get their inputs into it, as well as to have a “buy-in” of the plans, particularly of those Bank staff who are involved in marketing the loan facility.

With approval of the LPT, the TACT will be available to assist the Retail and Wholesale groups in moving the loan facility.  Assistance may include participation in client meetings, conduct of technical presentations about the project, and other activities as identified in the Strategic Marketing Plan.

### Task 7.  Technical Support on Sub-project Evaluation and Processing

While since the Project approval in 2009, the Bank staff on their own has already evaluated more than 35 projects, the TACT will still be providing technical assistance to the Bank in conducting sub-project evaluation.  Under Task 2, the TACT will prepare various sub-project evaluation tools and documents. These will be used in the evaluation of the various sub-projects submitted for possible funding.  As specified in the TOR, areas of evaluation will be on the project’s:

- Contribution to the efficiency in the transport and distribution of goods and services;

- Financial, economic, technical, safety, environmental, legal and policy considerations;

- Eligibility under LIDP;

- Appropriateness of the proposed technology;

- Cost efficiency, managerial and technical capability for proper operation and maintenance;

- Appropriate operation and effect indicators

- Risks and mitigating measures that can be employed to ensure sustainability and bankability

The assigned TACT specialist will conduct the sub-project assessment and will submit the reports.  As agreed with LPT, the TACT specialists will only be tapped for highly technical projects.  The DPM is expected to provide some assistance in the evaluation of minor projects.

| OUTPUTS: | - Call Reports (per sub-project/client) - Project Evaluation and Endorsement Reports (per sub-project) |
| --- | --- |

### Task 8.  Technical Assistance to End-users and/or Potential End-users

The TACT will be available to provide technical assistance to end-users (current or potential) as may be directed by the LPT.  Mainly, the assistance that will be provided will be on an advisory level in the areas of project preparation, such as on feasibility studies, detailed engineering designs, environmental impact assessment, and appropriate technologies. These assistance should be on specific concerns that will provide benefit to LIDP.

Training on certain topics will also be provided.  These are discussed under Task 10, Capacity Building.

### Task 9.  Project Monitoring and Reporting

Project monitoring activities are divided into two areas, monitoring of the overall Project implementation with regard to its objectives and targets; and sub-project progress monitoring.

Activity 9.1.  Development of a Monitoring and Evaluation (M&E) System with MIS

In order to have good monitoring of the Project implementation against its objectives and targets, a good Monitoring and Evaluation (M&E) system will need to developed and operationalize.  The M&E System will also need a good working management information system (MIS), which will be the repository of all project information. One of the priority activities of the TACT will be to develop and operationalize an M&E system with an MIS.  As specified in the TOR, the M&E system will include procedures for the collection and analysis of baseline data to determine attainment of project targets, in terms of its impact, outcome, output and other operation and effect indicators.

In preparing the M&E system, the TACT M&E Specialist will prepare the draft project logframe which will be subjected to a workshop within the Bank.  The preparation of M&E will need regular interactions between the M&E Specialist and the LPT.  All forms to be used for project M&E will be prepared and included in the Project M&E Manual.  Training will be conducted for specific Bank staff on the data collection and processing and on M&E reporting. Should DBP have an in-house M&E group, the TACT suggests that this group be involved in the entire process of M&E development.

Similarly, the preparation of the MIS will be coordinated with the DBP MIS group in order to ensure the integration of the system into the overall Bank MIS operation.  The operation and administration of the MIS will be discussed by the TACT with LPT and the DBP MIS group.  Hardware requirements will also be discussed and agreed upon.  Training on the operation and administration of the system will be conducted by the TACT for the identified MIS administrator.

| OUTPUTS: | - Project Logframe - Monitoring and Evaluation (M&E) System Manual - Management Information System (MIS) linked to DBP MIS, with technical and administration manual - Training on M&E and MIS |
| --- | --- |
| TIMELINE: | End of August to mid-October 2011 for M&E system Mid-September – end December for the MIS Training on M&E by early December 2011 |

Activity 9.2.  Preparation of Progress Reports

A list of project reports is presented in Table 3-2, under Section 3.  These reports will be prepared by TACT for consideration of LPT.  In addition, TACT will assist the Bank in the preparation of other reports such as those required by JICA and by NEDA.

The TACT will also assist LPT in formulating post-evaluation procedures that will be used later on, two (2) years after the LIDP closing date, to check and address if agreed target of operation and effect indicators are achieved for each sub-project.

At a certain period in project implementation, the TACT will conduct an analysis of the project implementation to determine the level of achievement of agreed targets of operation and effect indicators of the sub-projects.  Based on this evaluation, the TACT will prepare a recommendation of strategies and policies that will help push up the level of achievements of the indicators.

| OUTPUTS: | - Quarterly Progress Reports - Other reports required by JICA and NEDA - Assessment Report on the Level of Achievement of Sub-project Indicators |
| --- | --- |

Activity 9.3.  Sub Project Performance Monitoring

Performance monitoring procedures and guides are part of the initial list of management and monitoring tools that are immediately needed by the Project.  Thus, the TACT will prepare a manual for this purpose.  The manual will be following the current performance monitoring procedure being applied by other projects such as the EDP.  Sub-project information gathered through this activity will form part of the MIS and will also be included in the M&E system.

| OUTPUTS: | Performance Monitoring Report (per sub-project) |
| --- | --- |

### Task 10. Capacity Building

The TACT understands that all training activities within the Bank will need to be coordinated with the Human Resources Department of the Bank.  Initially, the TACT Training Coordinator will discuss with HRD on the training needs of the Bank staff particularly those who are involved in promoting and marketing the Project.  These are the Retail and Wholesale Banking staff as well as PD1 staff.  The TACT Training Coordinator will work with the HRD to get some additional information that will be needed to come up with an appropriate training plan for the focus group. Based on this, the Training Coordinator will prepare a training program that will identify the types of training format and structure that are applicable to the concerned staff.  These may include workshops, seminars, hands-on works, field visits, assignments, and study visits.  These will be discussed and coordinated with the LPT and HRD.

Training objectives, descriptions, agenda, and target participants will be prepared by the concerned TACT Specialist in coordination with the Training Coordinator.  The assigned TACT Specialist will prepare the detailed training modules.  As may be possible and practicable, two or three training topics/subjects will be combined into 1 run. Whenever needed, the TACT will invite other resource persons upon approval of the LPT.

The initial training subjects may include:

- Project Management

Participants will be given an overview of project management in general, then focusing on LIDP, its scope, coverage, funding scheme, reporting requirements, assistance to be provided by the Tam, and other project information.

- Project Due Diligence Review

Course will enable the participant/trainee to review the technical, financial, economic, social and environmental aspect of the proposed project using the basic evaluation criteria and be able to conduct a risk analysis.

- Project Monitoring and Evaluation

Course will cover an overview of the M&E system in general, the LIDP M&E system requirements in particular, and basic tools in gathering information for the M&E

- Sub-project Technical Evaluation

Course will use the Technical Evaluation Guide as the main training material.  The course will introduce the basic aspects of technical evaluation of proposed projects, will introduce the participants on the application of the PEER in evaluating proposed projects

- Sub-project Performance Monitoring

Course will introduce Bank staff and clients on the purposes and objectives of sub-project performance monitoring and the monitoring and reporting requirements for projects financed using LIDP funds.

- Basic Operations and Maintenance of Facilities

Course will enable the participant/trainee to identify the basic operations and maintenance procedure of the facilities and equipment

These sets of trainings may also be provided to PFI staff depending on their interest.

For the end-users, including LGUs, GOCCs, and cooperating agencies, training modules on the following topics may be developed and conducted:

- Basic project management and monitoring

- Basic project development and preparation

- Environmental and social safeguards

Other types of training will be identified later.  As mentioned above, all trainings will be agreed with LPT and HRM.

| OUTPUTS: | - LIDP Training Program - Specific Training Modules, including training materials - Training Reports |
| --- | --- |
| TIMELINE | End of September to mid-November 2011 for the Training Program First run of training for DBP staff by early December 2011 Other schedules to be finalized in the training program |

## Priority Activities

In view of the delayed implementation of various TA tasks and activities after the TACT mobilization on April 1, 2011, BII proposes to immediately conduct the following key tasks and activities in the remaining five months of 2011 to catch up with the project implementation.  The following tasks and activities are planned to be completed by November 2011:

- Task 1, Activity 1.1 – Conduct of Rapid Assessment of the Sub-sectors

- Task 1, Activity 1.2 – Preparation of Strategic Marketing Plan

- Task 2, Activity 2.1 – Preparation of Sub-Project Management and Monitoring Tools

- Task 2, Activity 2.2 – Preparation of Project Implementation Plan

- Task 3, Activity 3.1 – Preparation of Promotions Plan, including promotional materials

- Task 9, Activity 9.1 – Preparation of Monitoring and Evaluation (M&E) System

- Task 10, Activity 10.1 – Preparation of Training Program

The other tasks and activities will also be initiated during the period.

By the end of 2011, the TACT aims to have completed the following deliverables:

- Rapid Assessment Report

- Strategic Marketing Plan

- Revised/Improved Project OPG

- Technical Evaluation Guide for LIDP Sub-Projects (including PEER and evaluation criteria)

- LIDP Sub-Project Performance Monitoring Guide (including performance monitoring indicators)

- Project Implementation Plan

- Project Promotions Plan (initial); including marketing materials

- One (1) Regional Industry Sector Conference

- Participation in Industry Association Conferences (1 or 2)

- Policy Papers (1 topic; to be decided based on results of rapid assessment)

- Policy Dialogues

- M&E system

- MIS system

- Quarterly Report (July – September 2011)

- Performance Monitoring Reports (per sub-project visited; target: 4 projects)

- Training Program

- Conduct of training workshop for Bank staff (2 topics: technical evaluation and performance monitoring)

It is to be noted that for the technical guides for sub-project evaluation and sub-project monitoring, the TACT intends to initially prepare, two generic guides, one each for the transport sector and the logistics sector.  These guides and the corresponding forms will be used for the sub-projects that are ready for review or monitoring during the period.  These guides will be continuously improved, and separate sub-project guides will be prepared by mid-2012.

An initial promotions plan will also be prepared to focus on the packaging, transport and distribution facilities, and the cold chain sub-sectors.   The overall promotions plan will be prepared as part of the marketing plan.

The DPM will have overall responsibility in managing these priority tasks.

The deliverables specified in the table are only for the period covered, which is from August – December 2011. A complete overall schedule is shown in the next Section.

| Task/Activities | Involved Specialist/s | Deliverables for the timeframe covered | Timeframe (August – December 2011) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |
| Task 1. Strategy Formulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1 Conduct of Rapid Assessment | Transport Planner/Specialist – Task Leader Logistics Planner/Specialist Institutional Specialists Project Manager (to provide international perspective and experience) | Rapid Assessment Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2 Preparation of Strategic Marketing Plan | Marketing Specialist – Task Leader Transport Planner/Specialist Logistics Planner/Specialist Institutional Specialists | Strategic Marketing Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2. Design of the Implementation Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1: Preparation of sub-project management and monitoring tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Review and improvement of OPG |  | Revised/Improved Project OPG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Preparation of Project Logframe |  | (Please see Task 9, Activity 9.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Preparation of Technical Evaluation Guide (each for transport and logistics) | Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist | Technical Evaluation Guide for LIDP Sub-Projects (including PEER and evaluation criteria) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Preparation of Sub-Project Performance Monitoring Guide (each for transport and logistics) | Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist | LIDP Sub-Project Performance Monitoring Guide (including performance monitoring indicators) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2: Preparation of Project Implementation Plan | DPM with inputs from all TACT members | Project Implementation Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3. Project Promotions and Roadshows |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1 Preparation of a Promotions Plan | Marketing Specialist and DPM | Project Promotions Plan (initial); including marketing materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2. Conduct of Regional Industry Conferences | DPM; Sub-sector Specialists | One (1) Regional Industry Sector Conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3 Participation in Industry Associations’ Conferences | DPM; Sub-sector Specialists | Participation in Industry Association Conferences (1 or 2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 4. Inter-agency Linkages and Coordination | DPM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5. Conduct of Policy Dialogues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5.1 Development of Policy Papers | Institutional Specialist Transport Planner/Specialist Logistics Planner/Specialist | Policy Papers (1 topic) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5.2 Conduct of Policy Dialogues | DPM Institutional Specialist Transport Planner/Specialist Logistics Planner/Specialist | Policy Dialogues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6. Technical Support on Sub-project Marketing | DPM; Sub-sector Specialists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 7. Technical Support on Sub-project Evaluation and Processing | Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 8. Technical Assistance to End-users and/or Potential End-users | Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 9. Project Monitoring and Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 9.1. Development of a Monitoring and Evaluation (M&E) System with MIS | M&E Specialist; MIS specialist; DPM | M&E system; MIS system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 9.2. Preparation of Progress Reports | DPM | Quarterly Report (July – September 2011) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 9.3. Sub Project Performance Monitoring | Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist | Performance Monitoring Reports (per sub-project visited; target: 4 projects) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 10. Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 10.1 Preparation of Training Program | DPM; Training Specialist; Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist | Training Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 10.2 Conduct of Trainings for DBP and PFIs | DPM; Training Specialist; Sub-sector Specialists; financial Specialist; Environmental and social assessment specialist | Conduct of training workshop (2 topics: technical evaluation and performance monitoring) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 10.3 Conduct of Trainings for end-users |  | None for the period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |