Logistics Infrastructure Development Project (LIDP)

Minutes of the Meeting

(LIDP Technical Assistance Consultant Team)

DATE:	20 December 2011				VENUE:   4F Training Room, DBP

TIME STARTED: 9:37 AM				TIME FINISHED: 10:30 AM

PRESENT WERE:

| LIDP Technical Assistance Consultant Team (LIDP-TACT) - Mr Antonio Rex S. Chan - Ms Marissa V. David - Dr. Deo Leo Manalo - Engr. Cesar F. Domingo - Ms Preciousa Contreras - Engr. Francis C. Carlos | - Engr. Teddy San Juan - Engr. Danilo M. Laureta - Engr. Juanito P. Buduan - Engr. Gudmund Rognstad - Mr. Arnold T. Abuyog |
| --- | --- |

PURPOSE OF THE MEETING:

To discuss the schedules for the last quarter of 2011.

CALL TO ORDER:

The meeting was presided by Mr Antonio Rex Chan and was called to order at 9:37 AM

PARTICULARS:

- The submitted revised schedule for submission of the deliverables of the LIDP-TACT approved by the DBP was discussed to remind the LIDP-TACT regarding the deliverables and to have a wrap-up meeting for the year.

- On the Regional Industry Conference, the LIDP-TACT could check on the schedule of conferences of the following: Supply-Chain Association of the Philippines (SCAP), Department of Agrarian Reform (DAR), Department of Agriculture (DA), and Department of Trade and Industry (DTI). It was suggested that it would be better if the LIDP-TACT could identify four (4) or more conference every year. Ms Contreras, Training Specialist is to help identify possible conferences for the industry conference.

- The policy papers are based on the recommendation on the Rapid Assessment Report (RAR). It was mentioned that during the life of the project, there could be three (3) policy papers created which would mean that there would be one (1) policy paper per year.

- Strategies or Policy Recommendations on overcoming achievement of agreed targets of operation and effect indicators is more of DBP’s project implementation. This would be conducted on the middle of the project implementation and would serve as Mid-Term Review for the LIDP.

| Deliverable | Date of Submission |
| --- | --- |
| Rapid Assessment Report | Final Report End of December 2011 upon the compliance to the comments of the DBP |
| Sub-project Performance Monitoring Guides (Transport and Logistics) | End of December 2011 |
| Monitoring and Evaluation System | End of December 2011 |
| Training Program | Initial Draft Mid January 2012 Final Draft End of January 2012 |

ADJOURNMENT OF MEETING

- The meeting was adjourned at 10:30 AM.

Prepared By:							Reviewed by:

ARNOLD T. ABUYOG						ANTONIO REX S. CHAN

Project Coordinator						Deputy Project Manager

Noted by:

AVP MARIA DEL CARMEN H. HERNANDEZ

Deputy Program Manager