Logistics Infrastructure Development Project (LIDP)

Minutes of the Meeting

(LIDP Technical Assistance Consultant Team)

DATE:	22 November  2011				VENUE:   4F Training Rm, DBP Head Office

TIME STARTED: 10:15 AM				TIME FINISHED: 12:00 PM

PRESENT WERE:

| LIDP Technical Assistance Consultant Team (LIDP-TACT) - Ms Marissa V. David - Engr. Francis C. Carlos - Engr. Alfredo P. Ocampo - Engr. Danilo M. Laureta - Dr. Deo Leo Manalo - Engr. James Dexter Grageda | - Engr. Teddy San Juan - Engr. Antonio E. Kaimo - Mr. Noriel Sicad - Ms. Aniceta Mago - Mr. Arnold T. Abuyog |
| --- | --- |

PURPOSE OF THE MEETING:

To discuss updates and status of individual tasks and assignments

CALL TO ORDER:

The meeting was presided by Ms. Marissa David and was called to order 10:15 AM.

PARTICULARS:

- Comment(s) of PD/LPT on the Draft Final Rapid Assessment Report (RAR) are not yet received by the LIDP-TACT. The draft final report was submitted last 18 October 2011. It is suggested that a follow-up be made so that the final RAR can already be prepared and submitted. Dr. Deo Manalo mentioned that he would need the RAR for the preparation of Project Implementation Plan (PIP) and Policy Papers and dialogues. Other project outputs are also dependent on the RAR, and thus its earliest acceptance/approval by PD/LPT is needed.

- Considering the status of the various project deliverables particularly the RAR and OPG, which are the key precursor to the other deliverables, changes on the schedule of submission of deliverables were recommended. (See Attachment 1 for the Recommended Revised Schedule).

- Engr. Grageda was following up on the status of his request for the IT equipment. He said these are needed as soon as possible so that the system he had developed can already be downloaded and used at the project office.

- Ms. Mago submitted her first draft of the “Project Sub-Sector 1: Road Roll-on, Roll-off Terminal System (RRTS).

- Resolutions:

  - LIDP-TACT to inquire on the status of the RAR review and comments

  - LIDP-TACT to PD/LPT requesting approval of the revised schedule of deliverables.

  - Engr. Kaimo to submit inputs to TEG on the environmental and social component and to present on 29 November

  - Ms Mago to present the financial component of the TEG next meeting 29 November

  - Mr. “Casey”  to be requested to also present the technical portion of the Evaluation Guidelines on 29 November

  - Request DBP of the status of the Request Letter for the IT equipment to be used in the development of the M&E system and MIS. The submission of the MIS and M&E system is dependent on the procurement and installation of the equipment.

ADJOURNMENT OF MEETING

- The meeting was adjourned at 12:00 PM.

Prepared By:							Reviewed by:

ARNOLD T. ABUYOG						ANTONIO REX S. CHAN

Project Coordinator						Deputy Project Manager

Noted by:

SM MARIA DEL CARMEN H. HERNANDEZ

Deputy Program Manager

Attachment 1. Recommended Revised Schedule for the Submission of Deliverables on the LIDP-TACT.

| Deliverables | Schedule of Submission | Predecessors |
| --- | --- | --- |
| - Rapid Assessment Report | Draft Final Report October 2011 Final Report Mid December 2011 |  |
| - Strategic Marketing Plan | Mid December 2011 | - Rapid Assessment Report |
| - Revised Operating Policy Guidelines | Draft End of November 2011 | - INCEPTION Report |
| - Technical Evaluation Guides | Draft End November 2011 | - Revised Operating Policy Guidelines |
| - “Sub-Project” Performance Monitoring Guides | Mid December for the 2 Generic Guides Mid-2012 for the 5 sub-sector specific guides | - Technical Evaluation Guides |
| - Project Implementation Plan | End of December 2011 | - Rapid Assessment Report, - Revised Operating Policy Guidelines, - Strategic Marketing Plan |
| - Promotions Plan | *It was submitted Mid-October 2011. | - Project Implementation Plan, - Strategic Marketing Plan |
| - Regional Industry Conference on LIDP (at least 4 conferences) | One conference every Quarter of the Year | - Project Implementation Plan, - Promotions Plan |
| - Presentation Paper or Exhibit Materials for Sub-sector Industry Conferences | As needed | - Technical Evaluation Guides, - “Sub-Project” Performance Monitoring Guides, - Promotions Plan |
| - Policy Papers | To be identified and decided later | - Rapid Assessment Report, - DBP meetings |
| - M&E System | Draft End of November 2011 | - MIS System, - Technical Evaluation Guides, - “Sub-Project” Performance Monitoring Guides |
| - MIS System | End of January 2012 | - DPMS c/o DBP |
| - Strategies or Policy Recommendations on overcoming achievement of agreed targets of operation and effect indicators | Mid-Project (2013) | - Rapid Assessment Report |
| - Training Program | End of December 2011 | - Project Implementation Plan, |
| - Training Workshops for DBP and PFIs | End of January 2012 | - Project Implementation Plan, |
| - Training Workshops for end-users | First run by first semester of 2012; others to be scheduled | - Project Implementation Plan, |